## Obsidian TTS
Severity | Likelihood | Impact | STRIDE | Function | CWE | Risk Category | Technical Asset | Communication Link | RAA % | Identified Risk | Action | Mitigation | Check | ID | Status | Justification | Date | Checked by | Ticket
Critical | Likely | High | Information Disclosure | Architecture | CWE-312 | T1 API Key Plaintext in data.json | Obsidian Vault Storage |  | 100 | API key persisted plaintext in local vault settings | Avoid plaintext secret persistence; use OS keychain or encrypted-at-rest storage with access controls. | Migrate API key storage from `data.json` to keychain-backed storage and scrub legacy values. | Verify no plaintext API key remains in vault `.obsidian/plugins/*/data.json` files. | t1-api-key-plaintext-data-json@obsidian-vault-storage@local-user-workstation@elevenlabs-api-key | Accepted | saveData() serialises apiKey into data.json as a plain string. The Obsidian platform provides no secret store, so plaintext persistence is an unavoidable platform constraint. A security notice is displayed to the user in the settings tab (src/settings.ts). No code change can fully mitigate this within the plugin model; documented as accepted risk. | 2026-04-03 | vonst | T1
Elevated | Unlikely | Very High | Tampering | Operations | CWE-1008 | Missing Cloud Hardening |  |  | 0 | Missing Cloud Hardening risk at ElevenLabs Cloud | Cloud Hardening | Apply hardening of all cloud components and services, taking special care to follow the individual risk descriptions (which depend on the cloud provider tags in the model). <br><br>For <b>Amazon Web Services (AWS)</b>: Follow the <i>CIS Benchmark for Amazon Web Services</i> (see also the automated checks of cloud audit tools like <i>"PacBot", "CloudSploit", "CloudMapper", "ScoutSuite", or "Prowler AWS CIS Benchmark Tool"</i>). <br>For EC2 and other servers running Amazon Linux, follow the <i>CIS Benchmark for Amazon Linux</i> and switch to IMDSv2. <br>For S3 buckets follow the <i>Security Best Practices for Amazon S3</i> at <a href="https://docs.aws.amazon.com/AmazonS3/latest/dev/security-best-practices.html">https://docs.aws.amazon.com/AmazonS3/latest/dev/security-best-practices.html</a> to avoid accidental leakage. <br>Also take a look at some of these tools: <a href="https://github.com/toniblyx/my-arsenal-of-aws-security-tools">https://github.com/toniblyx/my-arsenal-of-aws-security-tools</a> <br><br>For <b>Microsoft Azure</b>: Follow the <i>CIS Benchmark for Microsoft Azure</i> (see also the automated checks of cloud audit tools like <i>"CloudSploit" or "ScoutSuite"</i>).<br><br>For <b>Google Cloud Platform</b>: Follow the <i>CIS Benchmark for Google Cloud Computing Platform</i> (see also the automated checks of cloud audit tools like <i>"CloudSploit" or "ScoutSuite"</i>). <br><br>For <b>Oracle Cloud Platform</b>: Follow the hardening best practices (see also the automated checks of cloud audit tools like <i>"CloudSploit"</i>). | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | missing-cloud-hardening@elevenlabs-cloud | Unchecked
Elevated | Very Likely | Medium | Spoofing | Development | CWE-434 | Missing File Validation | Obsidian Plugin Runtime |  | 46 | Missing File Validation risk at Obsidian Plugin Runtime | File Validation | Filter by file extension and discard (if feasible) the name provided. Whitelist the accepted file types and determine the mime-type on the server-side (for example via "Apache Tika" or similar checks). If the file is retrievable by endusers and/or backoffice employees, consider performing scans for popular malware (if the files can be retrieved much later than they were uploaded, also apply a fresh malware scan during retrieval to scan with newer signatures of popular malware). Also enforce limits on maximum file size to avoid denial-of-service like scenarios. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | missing-file-validation@obsidian-plugin-runtime | Unchecked
Elevated | Likely | Medium | Tampering | Operations | CWE-16 | Missing Hardening | Obsidian Vault Storage |  | 100 | Missing Hardening risk at Obsidian Vault Storage | System Hardening | Try to apply all hardening best practices (like CIS benchmarks, OWASP recommendations, vendor recommendations, DevSec Hardening Framework, DBSAT for Oracle databases, and others). | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | missing-hardening@obsidian-vault-storage | Unchecked
Elevated | Likely | High | Information Disclosure | Development | CWE-22 | Path-Traversal | Obsidian Plugin Runtime | Read or Write Vault Files | 46 | Path-Traversal risk at Obsidian Plugin Runtime against filesystem Obsidian Vault Storage via Read or Write Vault Files | Path-Traversal Prevention | Before accessing the file cross-check that it resides in the expected folder and is of the expected type and filename/suffix. Try to use a mapping if possible instead of directly accessing by a filename which is (partly or fully) provided by the caller. When a third-party product is used instead of custom developed software, check if the product applies the proper mitigation and ensure a reasonable patch-level. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | path-traversal@obsidian-plugin-runtime@obsidian-vault-storage@obsidian-plugin-runtime>read-or-write-vault-files | Unchecked
Elevated | Very Likely | Medium | Elevation of Privilege | Architecture | CWE-501 | Unguarded Access From Internet | Obsidian Vault Storage | Read or Write Vault Files | 100 | Unguarded Access from Internet of Obsidian Vault Storage by Obsidian Plugin Runtime via Read or Write Vault Files | Encapsulation of Technical Asset | Encapsulate the asset behind a guarding service, application, or reverse-proxy. For admin maintenance a bastion-host should be used as a jump-server. For file transfer a store-and-forward-host should be used as an indirect file exchange platform. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | unguarded-access-from-internet@obsidian-vault-storage@obsidian-plugin-runtime@obsidian-plugin-runtime>read-or-write-vault-files | Unchecked
Medium | Unlikely | Medium | Tampering | Architecture | CWE-1127 | Missing Build Infrastructure | Obsidian Plugin Runtime |  | 46 | Missing Build Infrastructure in the threat model (referencing asset Obsidian Plugin Runtime as an example) | Build Pipeline Hardening | Include the build infrastructure in the model. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | missing-build-infrastructure@obsidian-plugin-runtime | Unchecked
Medium | Unlikely | Medium | Spoofing | Architecture | CWE-287 | Missing Identity Store | Obsidian Plugin Runtime |  | 46 | Missing Identity Store in the threat model (referencing asset Obsidian Plugin Runtime as an example) | Identity Store | Include an identity store in the model if the application has a login. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | missing-identity-store@obsidian-plugin-runtime | Unchecked
Medium | Unlikely | Medium | Elevation of Privilege | Operations | CWE-1008 | Missing Network Segmentation | Obsidian Vault Storage |  | 100 | Missing Network Segmentation to further encapsulate and protect Obsidian Vault Storage against unrelated lower protected assets in the same network segment, which might be easier to compromise by attackers | Network Segmentation | Apply a network segmentation trust-boundary around the highly sensitive assets and/or datastores. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | missing-network-segmentation@obsidian-vault-storage | Unchecked
Medium | Unlikely | Medium | Elevation of Privilege | Business Side | CWE-308 | Missing Two-Factor Authentication (2FA) | Obsidian Plugin Runtime | Trigger TTS Command | 46 | Missing Two-Factor Authentication covering communication link Trigger TTS Command from Obsidian End User to Obsidian Plugin Runtime | Authentication with Second Factor (2FA) | Apply an authentication method to the technical asset protecting highly sensitive data via two-factor authentication for human users. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | missing-authentication-second-factor@obsidian-end-user>trigger-tts-command@obsidian-end-user@obsidian-plugin-runtime | Unchecked
Medium | Unlikely | Medium | Information Disclosure | Architecture | CWE-522 | Missing Vault (Secret Storage) | Obsidian Vault Storage |  | 100 | Missing Vault (Secret Storage) in the threat model (referencing asset Obsidian Vault Storage as an example) | Vault (Secret Storage) | Consider using a Vault (Secret Storage) to securely store and access config secrets (like credentials, private keys, client certificates, etc.). | Is a Vault (Secret Storage) in place? | missing-vault@obsidian-vault-storage | Unchecked
Medium | Unlikely | High | Information Disclosure | Operations | CWE-311 | Unencrypted Technical Assets | Obsidian Plugin Runtime |  | 46 | Unencrypted Technical Asset named Obsidian Plugin Runtime | Encryption of Technical Asset | Apply encryption to the technical asset. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | unencrypted-asset@obsidian-plugin-runtime | Unchecked
Medium | Unlikely | High | Information Disclosure | Operations | CWE-311 | Unencrypted Technical Assets | Obsidian Vault Storage |  | 100 | Unencrypted Technical Asset named Obsidian Vault Storage missing enduser-individual encryption with data-with-enduser-individual-key | Encryption of Technical Asset | Apply encryption to the technical asset. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | unencrypted-asset@obsidian-vault-storage | Unchecked
Low | Unlikely | Low | Information Disclosure | Architecture | CWE-1008 | Wrong Communication Link Content | Obsidian End User | Trigger TTS Command | 1 | Wrong Communication Link Content (protocol type "in-process-library-call" does not match target technology type "desktop": expected "library") at Obsidian End User regarding communication link Trigger TTS Command | Model Consistency | Try to model the correct readonly flag and/or data sent/received of communication links. Also try to use communication link types matching the target technology/machine types. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | wrong-communication-link-content@obsidian-end-user@obsidian-end-user>trigger-tts-command | Unchecked
High | Likely | High | Tampering | Development | CWE-22 | T3 Audio Output Path Traversal | Obsidian Plugin Runtime |  | 46 | Potential traversal in mp3 vault write path | Canonicalize and validate output paths against vault root before write operations. | Enforce normalized allowlisted path segments and reject traversal patterns (`..`, absolute paths, mixed separators). | Unit and integration tests prove writes are constrained to vault root on all supported platforms. | t3-audio-output-path-traversal@obsidian-plugin-runtime@local-user-workstation@generated-audio-files | False Positive | createVaultDirectories (src/util/file.ts) and generateFilename are dead code — neither function is imported or called anywhere in the active codebase. No vault writes occur; audio plays entirely from an in-memory Blob URL (src/util/audio.ts). Path traversal via vault writes is not possible in the current implementation. | 2026-04-03 | vonst | T3
High | Likely | High | Information Disclosure | Development | CWE-532 | T8 API Key Leakage in Logs | Obsidian Plugin Runtime |  | 46 | Sensitive auth material written to plugin logs | Redact secrets and prohibit logging of authorization headers and raw config blobs. | Centralized logger with redaction patterns and secure debug-mode gating. | Automated tests assert log output never contains key patterns or auth header values. | t8-api-key-logging-leak@obsidian-plugin-runtime@local-user-workstation@elevenlabs-api-key | False Positive | There are no console.log calls anywhere in the project. All logging uses console.error and none of those call sites include this.secrets.apiKey or any request headers — only generic status messages and caught error objects are logged. Confirmed clean. | 2026-04-03 | vonst | T8